International School

CDIO Project

# CMU-CS 447 JIS

Project Plan

Version 1.1

Date: March 8th, 2026

Smart Traffic Management System

Submitted by

Thong, Nguyen Cao

Thien, Luu Vu

Thong, Le Huu

Bao, Nguyen Gia

Approved by

MSc Huy, Truong Dinh

Proposal Review Panel Representative:

Name	Signature	Date

# CDIO Project - Mentor:

Name	Signature	Date

PROJECT INFORMATION

| Project acronym | STMS |  |  |
| --- | --- | --- | --- |
| Project Title | Smart Traffic Management System |  |  |
| Start Date | 09 Jan 2026 | End Date | 09 Mar 2026 |
| Lead Institution | International School, Duy Tan University |  |  |
| Project Mentor | MSc Huy, Truong Dinh |  |  |
| Scrum master / Project Leader & contact details | Thong, Nguyen Cao Email: pandatech0610@gmail.com Tel: 0934909569 |  |  |
| Partner Organization | Duy Tan University |  |  |
| Project Web URL |  |  |  |
| Team members | Name | Email | Tel |
|  | Thong, Nguyen Cao | pandatech0610@gmail.com | 0934909569 |
|  | Thien, Luu Vu | warface2005tk@gmail.com | 0919324219 |
|  | Thong, Le Huu | bass030196@gmail.com | 0768463655 |
|  | Bao, Nguyen Gia | ngbaog@gmail.com | 0938086668 |

DOCUMENT APPROVALS

The following signatures are required for approval of this document.

| Thong, Nguyen Cao Student ID: 29219053135 Scrum Master | Signature | Date |
| --- | --- | --- |
| Thien, Luu Vu Student ID: 29211140533 Team Member | Signature | Date |
| Thong, Le Huu Student ID: 29219038101 Team Member | Signature | Date |
| Bao, Nguyen Gia Student ID: 29219053725 Team Member | Signature | Date |

DOCUMENT NAME

| Document Title | Project Plan Document |  |  |
| --- | --- | --- | --- |
| Author(s) | 3T1B Team |  |  |
| Role | Product Owner, Team Member, Scrum Master |  |  |
| Date | March 8th, 2026 | File name: | ProjectPlan_STMS.doc |

REVISION HISTORY

| Version | Person(s) | Date | Description |
| --- | --- | --- | --- |
| 1.0 | Nguyen Cao Thong | 8-Mar-2021 | Create Project plan document |

TABLE OF CONTENTS

- Introduction:	6

  - Purpose:	6

  - Project Overview:	6

  - Project Deliverable:	6

- Team Organization:	6

  - Scrum Team Information:	6

  - Role and Responsibility:	7

  - Communication Methodology:	8

  - Communication and Report:	8

- Development Process:	9

- Schedule and Cost:	10

  - Detailed Schedule	10

  - Cost:	16

- Project Risk:	17

- Deliverables	18

- Introduction:

## Purpose:

This document provides a summary of the project's objectives, division of work, the major milestones, required resources, time and overall schedule and budget allocation used and based on the document proposal to build the Smart Traffic Management System (STMS) on time, according to the requirements and plan.

## Project Overview:

    - Reference to Proposal_STMS.docx

## Project Deliverable:

    - The project will be implemented for users such as admin, management department, user.

# Team Organization:

## Scrum Team Information:

### Table 1: Scrum Team Organization.

| Full Name | Phone | Email | Position |
| --- | --- | --- | --- |
| MSc Huy, Truong Dinh | 0982132352 | truongdinhhuy@dtu.edu.vn | Mentor |
| Thong, Nguyen Cao | 0934909569 | pandatech0610@gmail.com | Scrum Master |
| Thien, Luu Vu | 0919324219 | warface2005tk@gmail.com | Member |
| Bao, Nguyen Gia | 0938086668 | ngbaog@gmail.com | Member |
| Thong, Le Huu | 0768463655 | bass030196@gmail.com | Member |

## Role and Responsibility:

### Table 2: Role and Responsibilities.

| Role | Responsibility | Name/Title |
| --- | --- | --- |
| Product Owner | - Understand the user and customers with their needs. - Collaborate with the development team. - Manage the stakeholders. - Describe the user experience and product features. - Provides detail user stories. | Duy Tan University |
| Scrum Master | - Communicate the value of Scrum - Teach the organization on Scrum to maximize business value - Attend all Scrum meetings - Preserve the integrity and spirit of the Scrum framework - Maintain the focus of the Team - Make the Team aware of impediments and facilitate efforts to resolve them - Serve as a coach and mentor to members of the Team - Respectfully hold the Team, Product Owner and Stakeholders accountable for their commitments - Continually work with the Team and business to find and implement improvements | Thong, Nguyen Cao |
| Scrum Team | - Record the content of group meetings and activities of the member - Review documents - Analysis of the functions and requirements of the product. - Code and test. - Fix error. - Gather user stories. - Analysis user story to do specify Document. - Do the Test plan - Creation of test designs, test processes, test cases and test data. - Carry out testing as per the defined procedures. - Graph the results and make sure people know when test results decline. - Prepare all reports related to software testing carried out. - Analysis and evaluate the Test result. - Ensure that all tested related work is carried out as per the defined standards and procedures. | All Members |
| Mentor | - Guide on the process. - Monitoring all activities of Team. - Help with anything. | MSc Huy, Truong Dinh |

## Communication Methodology:

### Table 3: Communication Methodology.

| Audience/ Attendees | Topic/ Deliverable | Frequency | Method |
| --- | --- | --- | --- |
| Mentor and Team member | Project Progress Review | Weekly | Meeting, Email, Zalo |
| Team Member | Project Progress Review and Daily Meeting | Weekly | Jira, GitHub, Discord |

## Communication and Report:

### Table 4: Communication and Report.

| Type of communication | Methods, tools | Frequency | Information | People |
| --- | --- | --- | --- | --- |
| Communication among in group |  |  |  |  |
| Scrum meeting | Face to face or Hangouts | Every 3 days | Informed about what was done in the last 72 hours, working on plans for today, the difficulties encountered and the solutions required, just meeting 20-25 minutes. | Project team |
| Sprint Planning Meeting | Meet face to face | 2 weeks | All members in team together to analyze the requirements, functions, working on the sprint going to do, planning and design for the sprint. | Project team |
| Retrospective meeting | Meet face to face | Weekly | Complete documentation. For each stage, sharing materials, given the strengths and weaknesses for each. Period for each member and the solution calculated measurement project. | Project team and Mentor |
| Demo | Meeting online | Every 3 days | A web-based task tracking system. To manage or divide task, report bugs/issues. | Project team. |

# Development Process:

Scrum Process

- Scrum is an iterative and incremental agile software development framework for managing software projects and product or application development.

- Scrum focuses on project management institutions where it is difficult to plan.

- Mechanisms of empirical process control, where feedback loops that constitute the core management technique are used as opposed to traditional command-and- control management.

- Its approach to planning and managing projects is by bringing decision-making authority to the level of operation properties and certainties.

Benefit of the methodology:

−	Project can respond easily to change.

−	Problems are identified early.

−	Customers get the most beneficial work first.

−	Work done will better meet the customer’s needs.

−	Improved productivity.

−	Ability to maintain a predictable schedule for delivery.

# Schedule and Cost:

## Detailed Schedule:

|  | No. | Task Name | Start | Finish | Effort |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | 1 | Initial | 09/01 | 16/01 | 13 hrs |  |
|  | 1.1 | Gathering Requirement | 09/01 | 10/01 | 8 hrs |  |
|  | 1.1.1 | Get requirement from Mentor MSc Huy Truong Dinh | 09/01 | 10/01 | 4 hrs |  |
|  | 1.1.2 | Analyzing requirement | 09/01 | 10/01 | 4 hrs |  |
|  | 1.2 | Create Proposal Document | 16/01 | 16/01 | 5 hrs |  |
|  | 1.2.1 | Product Definition | 16/01 | 16/01 | 0.5 hrs |  |
|  | 1.2.2 | Business Need | 16/01 | 16/01 | 1 hrs |  |

| 1.2.3 | Prior Art | 16/01 | 16/01 | 0.5 hrs |
| --- | --- | --- | --- | --- |
| 1.2.4 | Proposed Solution | 16/01 | 16/01 | 1 hrs |
| 1.2.5 | Master Plan | 16/01 | 16/01 | 2 hrs |
| 2 | Start Up | 19/01 | 20/01 | 44 hrs |
| 2.1 | Project kick-off | 19/01 | 20/01 | 2 hrs |
| 2.2 | Create Document | 21/01 | 26/01 | 27 hrs |
| 2.2.1 | Project’s Meeting | 21/01 | 21/01 | 3 hrs |
| 2.2.2 | Create Project Plan | 22/01 | 23/01 | 6 hrs |
| 2.2.3 | Database Design | 24/01 | 25/01 | 10 hrs |
| 2.2.4 | User interface Design | 26/01 | 26/01 | 8 hrs |
| 3 | Development |  |  |  |
| 3.1 | Sprint 1 | 29/01 | 15/02 | 144 hrs |
| 3.1.1 | Sprint 1 Planning Meeting | 29/01 | 29/01 | 4 hrs |
| 3.1.2 | Create Sprint Backlog | 29/01 | 29/01 | 4 hrs |
| 3.1.3 | Create Database Document (Users, Camera) | 30/01 | 30/01 | 6 hrs |
| 3.1.4 | Create Test Plan Document for Sprint 1 | 30/01 | 31/01 | 6 hrs |
| 3.1.5 | Design | 31/01 | 31/01 | 8 hrs |
| 3.1.5.1 | UI Wireframes & System Architecture | 31/01 | 31/01 | 8 hrs |

| 3.1.6 | Coding | 01/02 | 12/02 | 92 hrs |
| --- | --- | --- | --- | --- |
| 3.1.6.1 | [Backend] Auth API (Login/Logout/Roles) | 01/02 | 02/02 | 12 hrs |
| 3.1.6.2 | [Admin] Manage Users & Camera Config | 02/02 | 04/02 | 16 hrs |
| 3.1.6.3 | [Core] Live Video Streaming Integration | 05/02 | 07/02 | 24 hrs |
| 3.1.6.4 | [AI] Vehicle Counting & Classification | 08/02 | 10/02 | 24 hrs |
| 3.1.6.5 | [AI] Speed Estimation Algorithm | 11/02 | 12/02 | 16 hrs |
| 3.1.7 | Testing & Fix Bug | 13/02 | 14/02 | 16 hrs |
| 3.1.7.1 | Execution Unit Test & Fix Bugs | 13/02 | 14/02 | 16 hrs |

| 3.1.8 | Release Sprint 1 | 15/02 | 15/02 | 8 hrs |
| --- | --- | --- | --- | --- |
| 3.1.8.1 | Sprint 1 Review Meeting | 15/02 | 15/02 | 4 hrs |
| 3.1.8.2 | Sprint 1 Retrospective | 15/02 | 15/02 | 4 hrs |
| 3.2 | Sprint 2 | 16/02 | 25/02 | 80 hrs |
| 3.2.1 | Sprint 2 Planning Meeting | 16/02 | 16/02 | 3 hrs |
| 3.2.2 | Create Sprint Backlog | 16/02 | 16/02 | 2 hrs |
| 3.2.3 | Update Database Document (Violations) | 16/02 | 16/02 | 3 hrs |
| 3.2.4 | Create Test Plan Document for Sprint 2 | 17/02 | 17/02 | 3 hrs |
| 3.2.5 | Design | 17/02 | 17/02 | 3 hrs |
| 3.2.5.1 | Design Violation Logic & Dashboard UI | 17/02 | 17/02 | 3 hrs |
| 3.2.6 | Coding | 18/02 | 23/02 | 50 hrs |
| 3.2.6.1 | [AI] Violation Detection (Red light/Lane) | 18/02 | 20/02 | 18 hrs |
| 3.2.6.2 | [Backend] Violation Logging & Video Evidence | 20/02 | 21/02 | 8 hrs |
| 3.2.6.3 | [Mgmt] Dashboard Stats & Video Player | 21/02 | 23/02 | 16 hrs |

| 3.2.6.4 | [Mgmt] Traffic Flow Configuration | 23/02 | 23/02 | 8 hrs |
| --- | --- | --- | --- | --- |
| 3.2.7 | Testing & Fix Bug | 07/05 | 08/05 | 8 hrs |
| 3.2.7.1 | Execution Integration Test & Fix Bugs | 24/02 | 24/02 | 8 hrs |
| 3.2.8 | Release Sprint 2 | 09/05 | 10/05 | 8 hrs |
| 3.2.8.1 | Sprint 2 Review Meeting | 25/02 | 25/02 | 4 hrs |
| 3.2.8.2 | Sprint 2 Retrospective | 25/02 | 25/02 | 4 hrs |
| 3.3 | Sprint 3 | 27/02 | 05/03 | 56 hrs |
| 3.3.1 | Sprint 3 Planning Meeting | 27/02 | 27/02 | 2 hrs |
| 3.3.2 | Create Sprint Backlog | 27/02 | 27/02 | 2 hrs |
| 3.3.3 | Update DB & Test Plan for Sprint 3 | 27/02 | 28/02 | 4 hrs |
| 3.3.5 | Design | 28/02 | 28/02 | 2 hrs |
| 3.3.5.1 | Design Map UI & Alert Popups | 28/02 | 28/02 | 2 hrs |
| 3.3.6 | Coding | 28/02 | 03/03 | 28 hrs |
| 3.3.6.1 | [Frontend] Leaflet Map & Camera Markers | 28/02 | 01/03 | 12 hrs |
| 3.3.6.2 | [AI/Sensor] Safety Detection (Fire/Flood) | 02/03 | 03/03 | 10 hrs |

| 3.3.6.3 | [System] Real-time Notifications | 03/03 | 03/03 | 6 hrs |
| --- | --- | --- | --- | --- |
| 3.3.5 | Testing & fix Bug | 04/03 | 05/03 | 10 hrs |
| 3.3.7.1 | UAT Testing & Final Bug Fixes | 04/03 | 05/03 | 10 hrs |
| 3.3.6 | Release Sprint 3 | 05/03 | 05/03 | 8 hrs |
| 3.3.6.1 | Sprint 3 Review Meeting (Final Demo) | 05/03 | 05/03 | 4 hrs |
| 3.3.6.2 | Sprint 3 Retrospective | 05/03 | 05/03 | 4 hrs |

## Cost

    - Cost Person/Hours

| Full Name | Role | Salary Rate (USD/hour) |
| --- | --- | --- |
| Thong, Nguyen Cao | Scrum Master | 6 |
| Thien, Luu Vu | Team Member | 6 |
| Bao, Nguyen Gia | Team Member | 6 |
| Thong, Le Huu | Team Member | 6 |

### Table 1. Cost person/hours

    - Total Cost Estimate

| No | Criteria | Price | Total (USD) |
| --- | --- | --- | --- |
| 1 | Working hours | 6 | 840 |
| 2 | Other cost | 100 | 400 |
|  |  |  | 1240 |

### Table 2. Total cost estimation

| Description | Amount | Unit |
| --- | --- | --- |
| Number of members | 4 | Person |
| Number of working hours per day | 3 | Hours |
| The cost per hour per member | 6 | USD |
| The number of working days | 58 | Days |

- The explanation for the table:

- Amount of working hours = 4 members * 3 hours * 90 days

- Other cost = 4 members * 100 USD

# Project Risk:

Table 7: Rating for likelihood and seriousness for each risk.

| RATING FOR LIKELIHOOD AND SERIOUSNESS FOR EACH RISK |  |  |  |
| --- | --- | --- | --- |
| L | Rated as Low | E | Rated as Extreme (Used for Seriousness only) |
| M | Rated as Medium | NA | Not Assessed |
| H | Rated as High |  |  |

Table 8: Project Risk.

| Risk | Definition | Level | Likelihood | Mitigation Strategy |
| --- | --- | --- | --- | --- |
| Leaflet API Integration | Difficulties in integrating Leaflet API to accurately display the live map and camera points. Potential issues with map loading speed or marker rendering. | H | M | Research Leaflet API documentation early. Create a prototype to test camera layer rendering before full implementation. |
| Real-time Video Latency | The "live video stream" provided by the Camera/Sensor may experience high latency, affecting the Management Department's ability to monitor violations in real-time. | E | H | Optimize video transmission protocols. Implement quality adjustment features (low resolution for preview, high resolution for details) to reduce load. |
| Notification Accuracy | Danger notifications (fire/flood) or violation detection logic may produce false positives due to sensor errors or environmental noise. | H | M | Conduct rigorous testing with simulated data scenarios. Allow the Admin to configure sensor sensitivity thresholds (Configuration camera/sensor). |
| Network | Block by Limited Bandwidth. High bandwidth consumption from multiple users viewing live video and maps simultaneously may cause system lag. | H | H | Upgrade transmission line network. Optimize data transfer and implement caching for static map resources. |
| Esmats of project planning | The plan may be delayed for the initial estimate of the project, especially regarding the complexity of video processing features. | L | L | Analysis of requirements and processes to ensure |
| Requirements | Internal contradictions that may exist in the request, specifically regarding permission conflicts between Admin and Management Department roles. | H | H | Uniform requirements prior to analysis. Create detailed User Stories for every role to ensure clarity. |
| Programming experience | Programming Languages and technology. The team may lack experience with streaming technology or map data management. | M | L | Experience sharing used to reduce the research time. Allocate time for R&D on key technologies. |
| System Security | Risks related to unauthorized access to the live camera feeds or Admin dashboard (manage users & roles). | E | M | Implement strong authentication/authorization protocols. Encrypt sensitive data transmission between sensors and the server. |

# Deliverables

Table 9: Deliverables

| No. | Document | Deadline | File Name |
| --- | --- | --- | --- |
| 1 | Proposal Document. | 9 –Mar – 2026 | Proposal_STMS.docx |
| 2 | Project Plan Document | 9 –Mar – 2026 | ProjectPlan_STMS.docx |